## Cover Sheet
Business case - Better data on Children in Care (Alpha)
April 2020
Project Description
This alpha project was a cross-council partnership led by GMCA and funded by the Local Digital Fund to improve the quality of data on children in care, to enable better evidence and improve support.
For more information on the solution evaluated in this business case, see our user research report
Overview of the business case
1. Summary: High level costs-benefits analysis of the solution over the next 5 years
2. Model: Detailed costs-benefits analysis of the solution over the next 5 years
3. Assumptions: inputs behind the model

## Summary
Summary
This business case studies the cost-benefits of the solution over the next 5 years, according to 3 uptake level scenarios: - Scenario A (downward): fail to scale to any councils beyond the alpha partners - Scenario B (conservative base case): scale to a third of councils in England - Scenario C (upward): scale to every council in England
Costs/benefits per year
5 years overview with the 3 scenarios - note the scenarios are plotted on different axes so the scale of the costs and benefits are fully visibile

## Model
Year | 2019 | 2020 | 2021 | 2022 | 2023 | 2024
Number of councils adopting the solution
Scenario A | 9 | 9 | 9 | 9 | 9 | 9
Scenario B | 9 | 9 | 25 | 50 | 50 | 50
Scenario C | 9 | 25 | 100 | 152 | 152 | 152
Costs
Discovery | 110000 | 0 | 0 | 0 | 0 | 0
Alpha | 0 | 100000 | 0 | 0 | 0 | 0
Beta | 0 | 229150 | 0 | 0 | 0 | 0
Ongoing costs | 0 | 0 | 19900 | 19900 | 19900 | 19900
Total costs | 110000 | 329150 | 19900 | 19900 | 19900 | 19900
Benefits
Benefits associated with time savings
Scenario A | 0 | 0 | 57317.625 | 57317.625 | 57317.625 | 57317.625
Scenario B | 0 | 0 | 159215.625 | 318431.25 | 318431.25 | 318431.25
Scenario C | 0 | 0 | 636862.5 | 968031 | 968031 | 968031
Benefits associated with reduction in number of children in care
Scenario A | 0 | 0 | 0 | 634500 | 634500 | 634500
Scenario B | 0 | 0 | 0 | 3525000 | 3525000 | 3525000
Scenario C | 0 | 0 | 0 | 10716000 | 10716000 | 10716000
Total benefits
Scenario A | 0 | 0 | 57317.625 | 691817.625 | 691817.625 | 691817.625
Scenario B | 0 | 0 | 159215.625 | 3843431.25 | 3843431.25 | 3843431.25
Scenario C | 0 | 0 | 636862.5 | 11684031 | 11684031 | 11684031
Costs-Benefits Analysis
Net benefits
Scenario A | -110000 | -329150 | 37417.625 | 671917.625 | 671917.625 | 671917.625
Scenario B | -110000 | -329150 | 139315.625 | 3823531.25 | 3823531.25 | 3823531.25
Scenario C | -110000 | -329150 | 616962.5 | 11664131 | 11664131 | 11664131
Cumulative net benefits
Scenario A | -110000 | -439150 | -401732.375 | 270185.25 | 942102.875 | 1614020.5
Scenario B | -110000 | -439150 | -299834.375 | 3523696.875 | 7347228.125 | 11170759.375
Scenario C | -110000 | -439150 | 177812.5 | 11841943.5 | 23506074.5 | 35170205.5
| Return on investment | Net present value
Scenario A | 4.6753 | 1318082.7371
Scenario B | 26.4372 | 9373851.9122
Scenario C | 81.087 | 29617199.2896

## Assumptions
Key
Inputs
Calculated inputs
Fixed assumptions
General assumptions
Solution development timeline
Year
Discovery | 2019
Alpha | 2020
Beta | 2020
Ongoing development: occurs every year, starting year | 2021
Number of councils adopting the solution
This business case studies the cost-benefits of the solution over the next 5 years, according to 3 uptake level scenarios: - Scenario A (downward): the number of councils keeps stable from alpha onwards - Scenario B (basecase): the number of councils adopting the tool increases after beta and reaches about a third of the councils in England (50) in year 4 - Scenario C (upward): the number of councils involved at the beta stage increases compared to alpha, and it keeps growing until all councils in England adopt the tool (152) in year 4
| Year -1 | Year 0 | Year 1 | Year 2 | Year 3 | Year 4
Scenario A (downward) | 9 | 9 | 9 | 9 | 9 | 9
Scenario B (basecase) | 9 | 9 | 25 | 50 | 50 | 50
Scenario C (upward) | 9 | 25 | 100 | 152 | 152 | 152
Modelling assumption
Discount rate (per annum) | 3.5% |  | Source: HMT Green Book discount rate
Costs assumptions
Discovery | 110000
Alpha | 100000
Beta
Beta - detailed costs
Costs - External provider's time | #days | Day rate* | Costs |  | *Day rates based on typical digital agency costs
Core tool build | 64 | 1000 | 64000
Rule implementation | 150 | 200 | 30000
User research | 40 | 650 | 26000
Design | 16 | 650 | 10400
Network engagement | 16 | 750 | 12000
Product management | 32 | 800 | 25600
Delivery management | 32 | 800 | 25600
Tech architect | 16 | 1300 | 20800
Contracting, data access and project administration | 15 | 650 | 9750
Accessibility audit |  |  | 5000
Total |  |  | 229150
Costs - Councils' time (in kind)
Contracting, procurement and data access | 20 | 208.6207 | 4172.4138 |  | Based on a £45,000 blended average annual salary for teams involved with a 21% overhead as assumed by the GDS benefits guidebook. Source: Manchester, Wigan and Stockport Councils.
Beta - total cash costs | 229150
Ongoing costs - fixed costs per annum (p.a.)
Ongoing - detailed costs
Product management | 5 | 800 | 4000 |  | Based on an assumption that an agency/contractor would charge £800 per day for a product manager role
Rule updating | 10 | 200 | 2000 |  | Based on an assumption that this workstream could be out-sourced to a low cost provider
Tool maintenance | 10 | 1000 | 10000 |  | Based on an assumption that an agency/contractor would charge £1000 per day for a senior developer role
User research | 6 | 650 | 3900 |  | Based on an assumption that an agency/contractor would charge £650 per day for a user researcher role
Ongoing - total costs | 19900 | p.a.
Benefits assumptions
Intro
We have developed a Theory of Change, illustrating the expected benefits of the solution
This business case is based on the monetarisation of 2 benefits of the tool ):
1. Time savings for analysts (medium impact, high certainty)
2. Reduction in number of children in care (high impact, low certainty)
Please note that this business case excludes many benefits, including the long term benefits on children and families, that are difficult to quantify and uncertain, but are likely to be very high. In that regard, this business case is conservative.
1. Benefits associated with time saving for analysts
Time savings
- The solution may allow councils to save time in errors identification, however it depends on councils (some were not doing anything outside of the DfE portal window, others had developed complex and time consuming ways of identifying errors outside of the DfE portal window). We assumed this benefit was too hypothetical to include it in this business case. - The time savings benefits presented here rely on one speciic feature of the tool, that facilitates the errors correction for the first type of errors = placement errors (37% of total errors).
% of errors that will benefit from simpler correction | 37%
We have detailed analysts' process for error cleaning of the 903 return data. The most time-consuming step of this process is step 4 = "Analysts find the right information and corrects the error". We are confident that the tool will nearly erase this step for placement errors, by suggesting the right answers based on Ofsted's database. We assume it would lead to 90% gain of time on cleaning placement errors.
Time savings on data cleaning for each of these errors | 90%
Total time savings to clean the SSDA 903 return / council | 33.3%
Modelling assumptions
Confidence factor - time savings | 85% |  | Using GDS benefits case confidence factor data we rated the data out of 5 on if it is current (5), relevant (5), range (3), quality (5), consistent (4). The additional research in alpha has enabled us to increase our confidence from ~65% in Discovery
Benefits occuring from year | 2021 |  | Analysts will be able to use the tool and save time immediately at the end of beta
Financial benefits - per council
The best quantified estimated of the cost of the children’s services returns comes from Gloucestershire County Council, who have outsourced the production of both their SSDA903 and CIN Census (the sister-return to the SSDA903, covering children in need) to a provider for £45,000 / year. This £45,000 figure is an underestimate of the true cost of these returns as A: Gloucestershire consider that this is cheaper than producing them in-house, B: Gloucestershire will still have to deploy some staff time to support the contractors in producing the returns. Analysts assess that the workload required for the SSDA903 and CIN Census returns are approximately equal, so we estimate the cost of the SSDA903 return as being £22,500 / council. These costs are consistent with our estimates across Stockport, Wigan and Manchester in Discovery.
Costs of cleaning the SSDA 903 return / council | 22500 | p.a.
Benefits attributable to the solution / council | 6368.625 | p.a.
2. Benefits associated with reduction in the number of children in care
Reduction in number of children in care - per council
Benefits of better use of data and evidence Case studies show that better use of data by leadership enables service improvement, leading to positive outcomes including a reduction in the number of children in care. Essex County Council and Newcastle City Council invested in data programmes to improve data analysis on one specific area (e.g. data analysis about needs of children on the “edge of care”), which led to a reduction of respectively 4% and 7% of children in care. This business case builds on these case studies. We assume that if a council improve its use of data analysis on 2 areas (e.g. needs about children on the edge of care + data about what interventions/ type of placement work best), services will improve and the number of children in care will reduced by 10% (4+7 = 11, rounded down to 10%).
Reduction of children in care attributable to better use of data | 10%
Role of data quality in improving better data Using wisely data and evidence to inform decision-making requires many components: To start with, councils need data: data needs to be collected, it needs to be consistently collected and to be high quality. Councils also need time, tools, and skills to analyse this data.Finally, there needs to be a data culture incentivising leadership to use data to inform decisions. Ensuring data quality non-only gives leadership more data (less incomplete datafields) and correct data, but it contributes to leadership trusting the data, which is key to change their behaviours and incentivise them to take data-informed decisions. To estimate the % of improvements (reduction in number of children in care) that is attributable to data quality, we asked the project teams in the two case studies (Essex and Newcastle) what proportion of the project work was data quality related. They estimated 10-15%, and we so took the lower bound for conservatism​:10%. We assume here that the ratio benefits/work is proportionate and that 10% of the work on data quality contributes to 10% of the outcomes (reduction in number of children in care).
% of this reduction attributable to better data quality | 10%
Total reduction attributable to better data quality | 1%
Modelling assumptions
Confidence factor - reduction in number of children in care | 30% |  | Using GDS benefits case confidence factor data we rated the data out of 5 on if it is current (4), relevant (2), range (2), quality (1), consistent (3) to give a confidence factor of 60%. We then halve this to account for the uncertainty around the estimate of the role of data quality in enabling analysis to give an overall 30% confidence factor​
Benefits occuring from year | 2022 |  | We estimated a one-year lag between the end of beta (when analysts will start using the tool) and the first benefits in reduction in number of children in care. We assumed that trust building and behaviour change for leadership will take a bit of time.
Financial benefits
Average spend on support for children in care per council​ | 23500000 | p.a. | There are 78,150 children in care across 152 children’s services departments, each costing councils an average of £45,647/year. Source: DfE Children’s Services Spending and Delivery statistics: https://www.gov.uk/government/publications/childrens-services-spending-and-delivery
Benefits attributable to the solution / council | 70500 | p.a.

## Sheet3 (hidden)
Net benefits
| -1 | 0 | 1 | 2 | 3 | 4
Scenario A | -110000 | -329150 | 37417.625 | 671917.625 | 671917.625 | 671917.625
Scenario B | -110000 | -329150 | 139315.625 | 3823531.25 | 3823531.25 | 3823531.25
Scenario C | -110000 | -329150 | 616962.5 | 11664131 | 11664131 | 11664131
Cumulative net benefits
| -1 | 0 | 1 | 2 | 3 | 4
Scenario A | -110000 | -439150 | -401732.375 | 270185.25 | 942102.875 | 1614020.5
Scenario B | -110000 | -439150 | -299834.375 | 3523696.875 | 7347228.125 | 11170759.375
Scenario C | -110000 | -439150 | 177812.5 | 11841943.5 | 23506074.5 | 35170205.5
Cost-analysis benefits per scenario
Scenario A
| -1 | 0 | 1 | 2 | 3 | 4
Costs | -110000 | -329150 | -19900 | -19900 | -19900 | -19900
Benefits | 0 | 0 | 57317.625 | 691817.625 | 691817.625 | 691817.625
Scenario B
| -1 | 0 | 1 | 2 | 3 | 4
Costs | -110000 | -329150 | -19900 | -19900 | -19900 | -19900
Benefits | 0 | 0 | 159215.625 | 3843431.25 | 3843431.25 | 3843431.25
Scenario C
| -1 | 0 | 1 | 2 | 3 | 4
Costs | -110000 | -329150 | -19900 | -19900 | -19900 | -19900
Benefits | 0 | 0 | 636862.5 | 11684031 | 11684031 | 11684031